## Project Action Plan
Retirement Planning Project Plan |  |  |  |  | Project start: | [7 empty] | 2025-01-27
[5 empty] | Display week: | [7 empty] | 1
[5 empty] | 2025-01-27 | [6 empty] | 2025-02-03 | [6 empty] | 2025-02-10 | [6 empty] | 2025-02-17 | [6 empty] | 2025-02-24
TASK | PROGRESS | START | END |  | 2025-01-27 | 2025-01-28 | 2025-01-29 | 2025-01-30 | 2025-01-31 | 2025-02-01 | 2025-02-02 | 2025-02-03 | 2025-02-04 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-08 | 2025-02-09 | 2025-02-10 | 2025-02-11 | 2025-02-12 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-16 | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-01 | 2025-03-02
[5 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Project Plan & Design
Review requirements | 100% | 2025-01-27 | 2025-01-30 | 4
Create ghantt chart to ouline tasks and timelines | 100% | 2025-01-30 | 2025-02-02 | 4
Identify key variables & relationships in retirement planning model | 100% | 2025-02-02 | 2025-02-05 | 4
Create a concept map | 100% | 2025-02-05 | 2025-02-07 | 3
Review the map & submit for feedback | 100% | 2025-02-07 | 2025-02-09 | 3
Execution
Review requirements & concept map | 100% | 2025-02-10 | 2025-02-11 | 2
Create initial structure of retirement planning model in Excel | 100% | 2025-02-11 | 2025-02-12 | 2
Ingest input parameters, decisions and calculations into the model | 100% | 2025-02-12 | 2025-02-14 | 3
Test and validate the model to ensure accuracy | 100% | 2025-02-14 | 2025-02-15 | 2
Submit model for feedback & make refinements | 100% | 2025-02-15 | 2025-02-16 | 2
Evaluation
Review Bob questions & personal case questions | 100% | 2025-02-17 | 2025-02-18 | 2
Analyze the Excel model results by capturing detailed responses to each case question | 100% | 2025-02-18 | 2025-02-19 | 2
Outline the structure of 6-to-9 page case paper | 100% | 2025-02-19 | 2025-02-20 | 2
Write the introduction, methodology, case questions and reflection sections | 100% | 2025-02-20 | 2025-02-22 | 3
Review answers for grammatical, citation errors and submit case paper for feedback | 100% | 2025-02-22 | 2025-02-23 | 2
Presentation
Create a PPT (PowerPoint) with 12-to-16 slides based on model, concept map and 6-to-9 page case paper | 100% | 2025-02-24 | 2025-02-25 | 2
Review PPT for clarity and ensure a coherent integration of concepts and images | 100% | 2025-02-25 | 2025-02-26
Do mock reharsal of screen recording & refine PPT | 100% | 2025-02-26 | 2025-02-27
Create a screen capture video of PPT in Panapto with explanation of 8 to 12 minutes in length | 100% | 2025-02-27 | 2025-02-28
Review recording and submit for feedback | 100% | 2025-02-28 | 2025-03-01 | 2
Insert new rows ABOVE this one